## Sheet1
Tasks | Start Date | Duration
A title page - Chris | 2017-08-27 | 12
Resumes of each group member - all members | 2017-08-28 | 9
Topic chosen - all members | 2017-08-27 | 12
WSD - Chris | 2017-08-28 | 9
Problem statement - Hafsah | 2017-09-08 | 14
Shall statements - Hafsah | 2017-09-10 | 15
RTM - the first 4 columns - Aqsa | 2017-09-10 | 14
Updated WSD - Chris | 2017-09-12 | 6
Gantt Chart showing allocation of task up to this point in the project - Parita | 2017-09-17 | 6
A dictionary explaining terms and computer jargons - Hena | 2017-09-14 | 7
A rational - Hafsah | 2017-09-09 | 12
Put the document together- all members | 19-Sept | 10